## README
Risk Governance OS – Excel MVP (v8, Table-free / Stable)
What changed in v8
This version removes Excel 'Table' objects to prevent file corruption during iterative model evolution. Functionality preserved: AB (Scenarios + TF default/override), CD (Erosion outputs + Summary), E (Field Guide + Input Form + Change Log + protections).
Core formulas
P_cum = 1 - (1 - P)^T L_exp = P_cum × I RE = L_exp × tau × TFi × (1 - C) TRE_i = RE × TF_used G = Σ TRE_i LR = G / A Scenario G_s = Σ [ L_exp × (tau×tau_mult) × (TFi×TFi_mult) × (1 - min(1,C×C_mult)) × TF_used ]
Backlog (future)
E+ (optional): stronger audit automation (requires VBA or external system), role-based access, and controlled submission workflow. Sensitivity analysis dashboard (LR elasticity by parameter) and structured scenario library.

## Field_Guide
Field Guide (What / Why / How to Fill)
Use this sheet as authoritative guidance for data entry and interpretation.
Field | Purpose (What it is) | Why it matters | How to fill (practical guidance) | Allowed / Typical Range | Example
Risk_ID | Unique identifier for a risk record | Enables traceability and stable ranking/aggregation | Use a short unique code. Do not reuse IDs across different risks. | Text; unique | R-SEC-001
Risk_Name | Short name for the risk | Used for Top-N outputs and executive communication | Use a concise name. Avoid long sentences. | Text | Credential leakage
Domain | Risk domain/category | Drives default TF_i and domain composition reporting | Select from dropdown. Maintain domain list in Setup. | Dropdown | Security
Description | Narrative description/context | Supports cross-domain translation and review | 2–5 lines: scenario, trigger, boundary, affected assets. | Free text | Leak via vendor VPN…
P | Per-cycle probability | Feeds cumulative probability over T | Enter 0–1 for one cycle. If unknown, estimate with notes. | 0–1 | 0.05
T | Exposure duration / cycles | Controls accumulation via P_cum | Integer ≥1 representing number of cycles/time units. | Integer ≥1 | 12
I | Impact magnitude (your unit) | With P_cum forms L_exp | Use same unit as capacity A (cost, points, normalized severity). | ≥0 | 250
C | Governance coverage | Directly reduces RE via (1−C) | 0–1. 0=no coverage, 1=full coverage. Be conservative unless verified. | 0–1 | 0.4
tau | Time pressure coefficient | Increases RE when rushed/late | >0. 1 neutral. >1 pressured; <1 improved cadence. | >0 | 1.2
TFi | Context difficulty coefficient | Captures structural difficulty | >0. 1 baseline. Increase for externalities/irreversibility/etc. | >0 | 1.1
TF_i | Manual type translation (override) | Allows expert override vs default | Leave blank to use TF_default. Fill only with justification in Notes. | Blank or >0 | 1.3
TF_default | Default TF_i from Domain | Reduces translation workload | Auto from Setup mapping; edit defaults in Setup if needed. | Auto | 1.3
TF_used | Effective TF applied | Ensures model runs even if TF_i blank | Auto: TF_i if provided else TF_default. | Auto | 1.3
P_cum | Cumulative probability over T | Implements accumulation logic | Auto: 1-(1-P)^T. | Auto | 0.46
L_exp | Expected loss pre-governance | Baseline exposure into governance layer | Auto: P_cum × I. | Auto | 115
RE | Residual Exposure | Core governance outcome per risk | Auto: L_exp × tau × TFi × (1−C). | Auto | 91
TRE_i | Typed Residual Exposure | Comparable/additive accountability unit | Auto: RE × TF_used. | Auto | 118
Erosion_Flag | Escalation indicator | Enables erosion-focused rollups (G_E, LR_E) | Choose E for escalating/compounding risks, N otherwise; justify in Notes. | E or N | E (Escalating)
Notes | Assumptions/sources/rationale | Auditability; reduces black-box perception | Record sources, estimation method, and overrides. | Free text | SME est., Q4…
TRE_score | Hidden helper for stable ranking | Prevents Top-N instability when ties exist | Auto/hidden; do not edit. | Auto

## Setup
Setup / Assumptions
Governance Capacity
A (Governance Capacity) | 100 | Input. Keep units consistent with I and L_exp.
Domains (dropdown list) |  | Erosion Flag (dropdown list)
Technology |  | E (Escalating)
Operations |  | N (Non‑Escalating)
Compliance
Security
Strategy
Supply Chain
Default TF_i by Domain (editable)
Domain | Default_TF_i
Technology | 1
Operations | 1
Compliance | 1.2
Security | 1.3
Strategy | 1.1
Supply Chain | 1.2

## Input_Form
Input Form (Fill one risk, then paste values into Risk_Register)
Instructions
1) Fill the blue cells below for ONE risk. 2) Copy A8:M8 and paste as VALUES into the next empty row in Risk_Register (columns A–M). 3) Do not paste into calculated columns; Risk_Register computes automatically.
Risk_ID | Risk_Name | Domain | Description | P | T | I | C | tau | TFi | TF_i | Erosion_Flag | Notes
Risk_ID | Risk_Name | Domain | Description | P | T | I | C | tau | TFi | TF_i | Erosion_Flag | Notes

## Risk_Register
Risk_ID | Risk_Name | Domain | Description | P | T | I | C | tau | TFi | TF_i | TF_default | TF_used | P_cum | L_exp | RE | TRE_i | Erosion_Flag | Notes | TRE_score
Note on E1: Per-cycle probability (0–1). Used with T to compute cumulative probability P_cum.
Note on F1: Exposure duration / number of cycles (integer ≥1).
Note on G1: Impact magnitude (unit consistent with A).
Note on H1: Governance coverage (0–1). RE is multiplied by (1−C).
Note on I1: Time pressure coefficient (>0). 1 neutral; >1 pressured; <1 improved cadence.
Note on J1: Context difficulty coefficient (>0). 1 baseline; >1 harder to govern.
Note on K1: Optional override for type translation. Leave blank to use TF_default.
Note on R1: E if escalating/compounding; N otherwise. Used for erosion rollups.

## Dashboard
Dashboard
Key Metrics |  | Top Risks by TRE_i |  |  | Erosion / Escalation Outputs
Total Governance Load (G) |  | Risk_Name | TRE_i | Domain | Metric | Value
Governance Capacity (A) |  |  |  |  | G_E (Σ TRE_i where E)
Risk Load Ratio (LR = G / A) |  |  |  |  | G_N (Σ TRE_i where N)
Active Risks (count) |  |  |  |  | %E of G
LR_E = G_E / A
Domain Composition (Σ TRE_i) |  |  |  |  | Erosion_Flag | Σ TRE_i
Domain | Σ TRE_i |  |  |  | E (Escalating)
Technology |  |  |  |  | N (Non‑Escalating)
Operations
Compliance
Security
Strategy
Supply Chain

## Scenarios
Scenario Comparison
How it works
Each scenario applies multipliers to governance parameters while keeping the same risk register. C_s = min(1, C × C_mult); tau_s = tau × tau_mult; TFi_s = TFi × TFi_mult. G_s = Σ [ L_exp × tau_s × TFi_s × (1 − C_s) × TF_used ]. LR_s = G_s / A_s. If A_s is blank, Setup!A is used.
Scenario Inputs
Scenario | A_s | C_mult | tau_mult | TFi_mult | G_s | LR_s | ΔLR vs Base
Base |  | 1 | 1 | 1
Scenario_1 |  | 1.1 | 1 | 1
Scenario_2 |  | 1 | 0.9 | 1
Scenario_3 |  | 1 | 1 | 0.9

## Summary
Summary Exports (Governance-ready)
Key Outputs |  |  | Domain × Σ TRE_i
G (Total) |  |  | Domain | Σ TRE_i
A (Capacity) |  |  | Technology
LR = G / A |  |  | Operations
G_E (Escalating) |  |  | Compliance
LR_E |  |  | Security
Strategy
Supply Chain
Top Risks (Stable by TRE_i)
Rank | Risk_ID | Risk_Name | Domain | TRE_i | Erosion_Flag
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Change_Log
Change Log (Audit Trail)
Record edits to risk inputs or governance assumptions. Without macros, Excel cannot automatically capture editor identity; treat this as an operational discipline. Tip: After entries, copy column B and paste values to freeze timestamps.
Change_ID | Date_Time | Editor | Risk_ID | Field | Old_Value | New_Value | Reason / Evidence | Scenario_Impacted (Y/N)